## WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
Establish a plant delivery and logistics plan | 1.1 | Hire delivery drivers | HR Specialist | 10 | HR Specialist manages hiring & develops training (with Training Manager)
| 1.2 | Source packaging materials | Fulfillment Director | 10 | Fulfillment Director sources materials, ensures equipment is functional, & confirms processes are correctly implemented
| 1.3 | Calculate delivery fees | Financial Analyst | 10 | Financial Analyst tracks and calculates costs and revenue
Select and install supply chain management software and equipment | 2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory Manager | 3 | Inventory Manager maintains inventory and oversees software installation
| 2.2 | Supervise vendor installation of fulfillment equipment | Fulfillment Director | 4 | Fulfillment Director sources materials, ensures equipment is functional, & confirms processes are correctly implemented
| 2.3 | Determine internal safety protocols | QA Tester | 10 | QA Tester ensures product quality & determines safety protocols & best practices
Develop and launch an employee training program | 3.1 | Develop training sessions | HR Specialist | 10 | HR Specialist manages hiring & develops training (with Training Manager)
| 3.2 | Train employees to use the software and equipment | Training Manager | 10 | Training Manager runs the training program on established protocols & refines the training process
| 3.3 | Monitor employee progress and improve training processes | Training Manager | 10 | Training Manager runs the training program on established protocols & refines the training process